MDB Econometrics – title, abstract, references, citations, links

Organisational Efficiency or Bureaucratic Quagmire: Do Quality-At-Entry Assessments Improve Project Performance?

Leonardo R. Corral

&

Nancy McCarthy

Pages 765-781 | Received 06 Nov 2017, Accepted 27 Oct 2018, Published online: 20 Dec 2018

- Cite this article

- https://doi.org/10.1080/00220388.2018.1554210

- CrossMark

- Full Article

- Figures & data

- References

- Supplemental

- Citations

- Metrics

- Reprints & Permissions

- Read this article

Share

- Back to Top

Abstract

Do quality-at-entry assessments enhance the delivery of development projects? In this paper we take advantage of approval and execution systems in place at the Inter-American Development Bank (IDB) to examine whether projects that have higher quality-at-entry – captured through grading scores provided by a checklist – perform better in terms of project implementation performance indicators. Implementation indicators include measures based on actual versus planned schedule of activities and cost outlays, as well as per cent of loan disbursed. The analysis suggests higher scores on project logic and economic analyses at entry have had a positive impact on project performance. However, monitoring and impact assessment scores had limited impacts on performance. The evidence supports the hypothesis that the use of a checklist can be an effective framework for assessing quality-at-entry for IDB projects, though there is scope to improve the checklist for certain indicators.

Acknowledgements

The authors would like to thank Shakirah Cossens, Diego Cortes, Ange Liu, and Luis F. Diaz for supporting data collection efforts, Carola Alvarez and Oscar Mitnik for helpful comments, and Josh Brubaker for excellent research assistance. We are grateful for the support of the Office of Strategic Planning and Development Effectiveness of the Inter-American Development Bank in conducting the study, and to participants of the SPD Half-Baked Lunch seminar series for their helpful comments.

Disclosure statement

No potential conflict of interest was reported by the authors. The opinions expressed in this publication are those of the authors and do not necessarily reflect the views of the Inter-American Development Bank, its Board of Directors, or the countries they represent.

Supplemental material

Supplementary Materials are available for this article which can be accessed via the online version of this journal available at https://doi.org/10.1080/00220388.2018.1554210

Notes

1. There are three sub-sections, with a third section that only needs to be assessed for ‘policy-based’ loans. We do not include these types of loans into this analysis.

2. Beginning in 2015, SPD has now categorised values greater than two as ‘outliers’. For our analysis, we use the original categories to develop our cost and schedule performance indicators.

3. We also ran all specifications using the average progress scores, which produced results very similar to results using the latest scores, so we choose to present results using latest scores. Results for average scores can be obtained from the corresponding author.

4. We tested for normality of the residuals using the ‘sktest’ command in STATA, which tests for skewness and kurtosis in the error distributions. We ran the tests because a number of observations are bunched at one, that is, where actual and planned performance coincide. Test results lead us to not reject normally distributed errors. To probe the robustness of results, we normalised all of the cost and schedule deviation variables, and ran generalised linear models (GLMs). The results for all GLMs are qualitatively very similar to the OLS results, thus we include only the OLS results here in the paper. Results can be obtained from the corresponding author.

5. We also ran the estimations using the ‘exchangeable’ structure, which produced similar results that can be obtained from the corresponding author.

Good countries or good projects? Comparing macro and micro correlates of World Bank and Asian Development Bank project performance

- Published: 05 September 2016

- Volume 12, pages 335–363, (2017)

- Cite this article

Top of Form

Save article

Bottom of Form

View saved research

The Review of International OrganizationsAims and scopeSubmit manuscript

- David Bulman,

- Walter Kolkma &

- Aart Kraay

- 1735 Accesses

- 65 Citations

- 4 Altmetric

- Explore all metrics

Abstract

This paper examines the micro and macro correlates of aid project outcomes in a sample of 3797 World Bank projects and 1322 Asian Development Bank projects. We find that project outcomes vary much more within countries than between countries: only 10–25 % of the variation in project outcomes is between countries, and the rest is within countries. Among country-level macro variables, GDP growth and the policy environment are significantly positively correlated with project outcomes. Among project-level micro variables, shorter project duration and the presence of additional financing are significantly correlated with better project outcomes. In addition, the track record of the project manager in delivering successful projects is highly significantly correlated with project outcomes. We find few significant differences between the two institutions in the relationship between these variables and project outcomes.

This is a preview of subscription content, log in via an institution  to check access.

Access this article

Log in via an institution

Subscribe and save

Springer+

from €37.37 /Month

- Starting from 10 chapters or articles per month

- Access and download chapters and articles from more than 300k books and 2,500 journals

- Cancel anytime

View plans

Buy Now

Top of Form

Buy article PDF 39,95 €

Bottom of Form

Price includes VAT (Australia)

Instant access to the full article PDF.

Institutional subscriptions

Similar content being viewed by others

Aid and institutions: Local effects of World Bank aid on perceived institutional quality in Africa

Article Open access25 November 2022

A New Model of Multilateral Development Bank: a Comparative Study of Road Projects by the AIIB and ADB

Article 07 November 2018

Macroeconomic Performance and Progress Towards a Circular Economy in Developing Countries

Chapter © 2023

Explore related subjects

Discover the latest articles, books and news in related subjects, suggested using machine learning.

- Cohesion

- Development Aid

- Development Economics

- Development Finance

- Project Management

- Development Studies

- Foreign Aid Dynamics and Development Outcomes

Notes

- For related work on this issue in a very different context of aid projects in different communities in Pakistan, see Khwaja (2009).

- World Bank projects can be assigned to multiple sectors, with an indication of the fraction of the project’s value in each sector. We follow DKK in assigning each project to its largest sector. In the ADB data we have information on only one sector per project, which is reflected in the table above.

- The lack of PCR ratings prior to 1995 explains the high share of projects (48 %) in our sample that receive detailed Project Performance Evaluation Reports (PPERs). From 1995 onwards, 292 out of 980 ADB projects have PPERs, for a rate of 30 % which is comparable to the WB.

- Average project success rates vary across sectors, and the sectoral composition of projects differs slightly between the ADB and the WB. However, these differences are sufficiently small that they do not account for much of the difference in overall project success rates between the two institutions. Assuming ADB sector success rates and applying the WB Asia sector distribution results in a success rate of 64.0 % compared to the ADB baseline of 64.5 %. Similarly, assuming the WB sector success rates and applying ADB sector distribution results in a success rate of 77.3 % compared to a WB Asia baseline of 78.2 %. The different treatment of sustainability issues in evaluations in the World Bank and ADB in the 2000s may also explain part of the difference. Sustainability sub-ratings are generally somewhat lower than overall ratings in the ADB.

- We cut off the analysis in 2007 due to the more limited number of projects to analyze from 2008 onwards, which artificially drives the R-squareds higher.

- Summary statistics on all variables used in the empirical analysis can be found in Appendix Table 1.

- We obtain broadly similar results if we use a linear probability model (as in DKK), or if we estimate an ordered probit model separately for the WB and the ADB, so as to use the information in the 1–6 scale of the WB and the 1–4 scale of the ADB ratings.

- As a further robustness check, we also estimated our specification for a sample that excluded ADB projects evaluated prior to 1995, in order to match the timing of the WB project sample. However, the results are very similar in this smaller sample, and so are not reported to conserve space.

- Note that since every variable in the regression, including the unreported sector and period dummies, enters both directly and as an interaction with a dummy for ADB projects, this means that our specification is equivalent to estimating separate regressions for the two institutions. We estimate the pooled regression with interactions only to facilitate testing the null hypothesis of equal slopes across the two institutions.

- The ADB produces a similar set of assessments, but only for poorer client countries eligible for concessional lending from the Asian Development Fund. In contrast, the WB produces its CPIA assessments for all clients, but discloses them publicly only for concessional borrowers. For concessional borrowers in Asia, the WB and ADB CPIA ratings are quite highly correlated.

- It is important to emphasize that we are looking at planned project length, not actual project length. Complex projects may get restructured or cut off and then rated unsuccessful. As components get canceled, the actual project length may be quite short.

- A potential concern here is that some of the difference between disbursements and commitments could reflect exchange rate fluctuations on loans denominated in currencies other than US dollars, that then are converted back to US dollars for recording purposes. To guard against this possibility, we also repeated our results, but dropping all log differences between disbursements and commitments that were less than 25 % in absolute value, so that the remaining “large” differences are more likely to be due to deliberate choices to scale down or scale up the project. Doing so has little effect on our results.

- Interestingly, investment lending projects tend to receive lower ratings in Columns (1) and (2) which do not include project-level controls -- indicating that investment lending projects tend to have other characteristics such as longer planned length and longer implementation delays that are associated with worse performance. Once these attributes are held fixed, investment lending projects do better on average. Note that this sign reversal holds true only for WB projects. In Columns (1) and (2) the ADB interaction enters significantly positively, and with an estimated coefficient that is larger in absolute value than the direct effect. This means that, even without controlling for other project characteristics, investment lending projects do not receive lower ratings on average in the ADB.

- Note that the figures in this sentence are not the inverses of the figures in the previous sentence. This is because the average across projects of years per project manager is not the same as the average across projects of project managers per year. Note also that our figure of average tenure of 1.9 years for the ADB, derived from 10 years of interim progress report data from 2000 onwards, is similar to 1.7 years found by an analysis of staff tenure data of 375 PVRs (IED 2015). This suggests that the limited availablility of pre-2000 data in our sample does not seriously affect our estimate of average turnover.

- This difference should not be over-interpreted as a sign of greater candor on the part of WB project managers, as it simply is an unconditional probability. Controlling for the same set of project characteristics included in the regressions in Table 2, we do not find that the rate of unsatisfactory self-assessments in the first half of project life is significantly different between the two institutions.

- Optimism bias is a well-known feature of project management (Flyvbjerg 2006; Siemiatycki 2010; Kolkma 1999).

- All World Bank projects in our sample have first half ratings. Including the warning ratings reduces the ADB sample significantly while including the project manager track record variable reduces the sample size for both institutions. The regression results reported below focus only on a sample with observations for both variables. Running separate regressions for each increases the number of observations but does not significantly alter the results.

- A potential concern here is that, despite the presence of country-level control variables in the regression, some project managers tend to work in “difficult” countries, and this in turn lowers the measured track record of the project manager. This however turns out not to be a factor -- the project manager track record variable remains strongly significant even when country fixed effects are included in the regressions.

- It is worth noting that including the first half interim project outcome ratings helps to control for some of the omitted variable bias problems that clouded the interpretation of other project-level correlates discussed above. This is because this indicator captures information observable to the project manager at the time about likely deficiencies in the project that are hard to measure ex post. The fact that coefficients on most of the other project-level variables retain their size and significance is therefore encouraging that these potential omitted-variable biases may not be too severe.

- Specifically, if  is the percent of the duration of project j for which i was the manager and PR j is the rating for project j, then our default measure of the track record of project manager i is:  and the track record of the project J management team is: . Alternative #1 excludes from R i all projects for which i was the last manager. Alternative #2 excludes the last project manager from the calculation of R J.

- While such turnover can be beneficial for the project in question, it may not be beneficial for the entire portfolio of projects the ADB or the WB are implementing. This aggregate effect will depend on both (a) what happens to the other projects the incoming project manager is also working on -- it could be that the additional claims of the new project on the project manager’s attention come at the expense of the other projects in his or her portfolio, and (b) what happens to the outgoing project manager, who may instead be put in charge of other projects.

References

- Chauvet, L., Collier, P. and Fuster, A. (2015). Supervision and project performance: A principal-agent approach. Working Papers DT/2015/04, DIAL (Developpement, Institutions et Mondialisation)

- Denizer, C., Kaufmann, D., and Kraay, A. (2013). Good Countries or Good Projects? Macro and Micro Correlates of World Bank Project Outcomes. Journal of Development Economics, 105, 288–302

- Dollar, D. and Levin, V. (2005). Sowing and reaping: institutional quality and project outcomes in developing countries, Policy Research Working Paper Series 3524, The World Bank.

- Dollar, D., & Svensson, J. (2000). What Explains the Success and Failure of Structural Adjustment Programs? The Economic Journal, 110, 894–917.

Article Google Scholar

- Flyvbjerg, B. (2006). From Nobel Prize to Project Management: Getting Risks Right. Project Management Journal, 37(3), 5–15.

Google Scholar

- Gelb, A. (2010). How can donors create incentives for results and flexibility for fragile states? A Proposal for IDA. Center for Global Development, Working Paper No. 227.

- Geli, P., Aart, K. and Hoveida, N. (2014). Predicting Active World Bank Project Outcomes. World Bank Policy Research Working Paper No. 7001.

- Guillaumont, P. and Laajaj, R. (2006). When Instability Increases the Effectiveness of Aid Projects. World Bank Policy Research Working Paper No. 4034.

- IED Independent Evaluation Department (2015). 2015 annual evaluation review. Manila: Asian Development Bank.

- Isham, J., & Kaufmann, D. (1999). The Forgotten Rationale For Policy Reform: The Productivity of Investment Projects. The Quarterly Journal of Economics, 114(1), 149–184.MIT Press

Article Google Scholar

- Isham, J., Kaufmann, D. and Pritchett, L. (1997). Civil Liberties, Democracy, and the Performance of Government Projects, World Bank Economic Review, 11(2), 219–242.

- Khwaja, A. I. (2009). Can Good Projects Succeed in Bad Communities?. Journal of Public Economics, 93, 899–916.

- Kilby, C. (2000). Supervision and Performance: The Case of World Bank Projects. Journal of Development Economics, 62, 233–259.

- Kilby, C. (2013). The Political Economy of Project Preparation: An Empirical Analysis of World Bank Projects. Journal of Development Economics., 105, 211–225.

- Kilby, C. (2015). The Impact of World Bank Preparation on Project Outcomes. Journal of Development Economics, 115, 111–123.

- Kolkma, W. (1999). Work in Progress: The Hidden Dimensions of Monitoring and Planning in Pakistan. West Lafayette: Purdue University Press.

Google Scholar

- Siemiatycki, M. (2010). Managing Optimism Biases in the Delivery of Large-Infrastructure Projects: A Corporate Performance Benchmarking Approach. European Journal of Transport and Infrastructure Research, 10(1), 30–41.

- Smets, L., Knack, S., & Molenaers, N. (2013). Political Ideology, Quality at Entry and the Success of Economic Reform Programs. The Review of International Organizations, 8, 447–476.

Article Google Scholar

- World Bank (1991). World Development Report 1991: The Challenge of Development. New York: Oxford University Press.

Book Google Scholar

Download references

Acknowledgments

The authors are grateful to Adele Casorla for help compiling the data of the Independent Evaluation Department of the Asian Development Bank, and to Adele Casorla, Luis Serven, Ganesh Rauniyar, Vinod Thomas, Jiro Tominaga, and Hans Van Rijn for helpful comments on earlier drafts, and to the Editor and two anonymous referees for very helpful feedback. The views expressed here are the authors’ and do not reflect the official views of the World Bank, the Asian Development Bank, their Executive Directors, or the countries they represent.

Author information

Authors and Affiliations

- Harvard Kennedy School, Cambridge, MA, 02138, USA

David Bulman

- World Bank, 1818 H Street NW, Washington D.C., USA

David Bulman & Aart Kraay

- Independent Evaluation, Asian Development Bank, Manila, Philippines

Walter Kolkma

Corresponding author

Correspondence to Aart Kraay.

Electronic Supplementary Material

ESM 1

(PDF .97 mb)

Appendix

Appendix

Table 6 Descriptive Statistics

Full size table

Rights and permissions

Reprints and permissions

About this article

Cite this article

Bulman, D., Kolkma, W. & Kraay, A. Good countries or good projects? Comparing macro and micro correlates of World Bank and Asian Development Bank project performance. Rev Int Organ 12, 335–363 (2017). https://doi.org/10.1007/s11558-016-9256-x

Table 6 Descriptive Statistics

From: Good countries or good projects? Comparing macro and micro correlates of World Bank and Asian Development Bank project performance

|  | World Bank |  |  | Asian Development Bank |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Mean | St. Dev. | Obs. | Mean | St. Dev. | Obs. |
| Success | 0.74 | 0.44 | 3797 | 0.65 | 0.48 | 1322 |
| CPIA rating | 3.44 | 0.50 | 3797 | 3.48 | 0.51 | 1322 |
| Real GDP per capita growth | 0.03 | 0.03 | 3797 | 0.04 | 0.03 | 1322 |
| Freedom House rating | 6.08 | 2.99 | 3797 | 4.91 | 2.62 | 1322 |
| Dummy for PAR/PPER evaluations | 0.27 | 0.44 | 3797 | 0.48 | 0.50 | 1322 |
| Dummy for ADB PVR evaluations | - | - | 3797 | 0.19 | 0.39 | 1322 |
| Log(total commitment) | 3.99 | 1.24 | 3797 | 4.07 | 1.01 | 1322 |
| Planned project length | 57.38 | 25.10 | 3797 | 51.33 | 18.24 | 1322 |
| Effectiveness delay | 6.54 | 4.61 | 3797 | 6.51 | 4.35 | 1322 |
| Implementation delay | 16.33 | 15.92 | 3797 | 23.23 | 23.87 | 1322 |
| Log(additional funding) | −0.15 | 0.41 | 3797 | −0.24 | 0.46 | 1322 |
| Project manager track record | 0.72 | 0.28 | 2373 | 0.68 | 0.28 | 367 |
| Project manager track record (alt. #1) | 0.71 | 0.32 | 1591 | 0.66 | 0.32 | 329 |
| Project manager track record (alt. #2) | 0.72 | 0.29 | 1591 | 0.68 | 0.29 | 329 |
| Project manager turnover | 0.43 | 0.22 | 2373 | 0.63 | 0.27 | 367 |
| Negative rating in first half | 0.13 | 0.33 | 2373 | 0.09 | 0.28 | 367 |

What Influences World Bank Project Evaluations?

- Chapter

- First Online: 07 September 2019

- pp 109–150

- Cite this chapter

Lessons on Foreign Aid and Economic Development

- Christopher Kilby &

- Katharina Michaelowa

- 1207 Accesses

- 18 Citations

Abstract

In 2011, the World Bank’s Independent Evaluation Group made its project ratings database public. With broad geographic and sectoral coverage, this database is a valuable resource for research on development effectiveness, what works and what does not. This chapter first provides an overview for scholars interested in evaluation but unfamiliar with the World Bank evaluation system. Next we examine whether geopolitical or institutional factors influence ratings. We focus on how projects are selected for performance assessments and what factors influence project ratings. We find evidence that bureaucratic factors influence selection and that one geopolitical variable—nonpermanent United Nations Security Council membership—impacts ratings. Nonetheless if researchers control for potential biases, World Bank project ratings can provide a valuable way to measure project quality in many applications.

This is a preview of subscription content, log in via an institution  to check access.

Access this chapter

Log in via an institution

Subscribe and save

Springer+

from €37.37 /Month

- Starting from 10 chapters or articles per month

- Access and download chapters and articles from more than 300k books and 2,500 journals

- Cancel anytime

View plans

Buy Now

Top of Form

- Available as PDF

- Read on any device

- Instant download

- Own it forever

Buy Chapter

Bottom of Form

Top of Form

- Available as EPUB and PDF

- Read on any device

- Instant download

- Own it forever

Buy eBook

Bottom of Form

Top of Form

- Compact, lightweight edition

- Dispatched in 3 to 5 business days

- Free shipping worldwide - see info

Buy Softcover Book

Bottom of Form

Top of Form

- Durable hardcover edition

- Dispatched in 3 to 5 business days

- Free shipping worldwide - see info

Buy Hardcover Book

Bottom of Form

Tax calculation will be finalised at checkout

Purchases are for personal use only

Institutional subscriptions

Similar content being viewed by others

Quantitative Risk Analysis for International Project Management and Programs in an Emerging Economy

Chapter © 2017

A View of the Global Scene

Chapter © 2018

The Independent Evaluation Group (IEG) of the World Bank Group: Influences on Evaluation Structures and Practices Globally and in the Americas

Chapter © 2022

Explore related subjects

Discover the latest articles, books and news in related subjects, suggested using machine learning.

- Performance Assessment

- Political Psychology

- Politics and International Studies

- Psychometrics

- Social Influence

- Social Perception

- Evaluation Practices in European Policy Making

Notes

- 1.

In response NGO and donor pressure, the World Bank has gradually increased the amount of information it makes public. The “Access to Information” policy adopted in 2010 under World Bank President Robert Zoellick marked a major step forward, providing access to new information on projects and putting in place procedures to request information and to appeal when requests are initially denied.

- 2.

Outsider papers: Buntaine and Parks (2013), Dreher et al. (2013), Girod and Tobin (2016), Kilby (2015), Malik and Stone (2018), Michaelowa and Borrmann (2006), Sud and Olmstead-Rumsey (2012), and Winters (2014). Insider papers: Blum (2014), Bulman et al. (2017), Chauvet et al. (2010), Chauvet et al. (2017), Cruz and Keefer (2013), Deininger et al. (1998), Denizer et al. (2013), Dollar and Levin (2005), Dollar and Svensson (2000), Geli et al. (2014), Guillaumont and Laajaj (2006), Isham and Kaufmann (1999), Isham et al. (1997), Kaufmann and Wang (1995), Limodio (2011), Malesa and Silarszky (2005), Moll et al. (2015), Pohl and Mihaljek (1992), Ralston (2014) and Smets et al. (2013).

- 3.

The influence of geopolitics has been demonstrated at every stage of the project cycle (preparation: Kilby (2013b); approval (number of loans): Dreher et al. (2009), Kaja and Werker (2010); disbursement (speed): Kilby (2013a); disbursement (enforcement of conditionality): Kilby (2009); disbursement (electioneering): Kersting and Kilby (2016)) except at the evaluation stage. Most of the literature focuses on US informal influence over the World Bank, which is headquartered just two blocks from the White House and depends on the US for funding and leadership.

- 4.

For a detailed history of OED, see Grasso et al. (2003). In the text below we use IEG to refer to the evaluation department even before 2005.

- 5.

This reduction was driven by an expanding World Bank project portfolio but also increasing demands on IEG to generate other products at the country and sector levels (Grasso et al. 2003). More than 70% of IEG’s budget was devoted to PPARs in 1976 (Grasso et al. 2003, 169); the figure was less than 10% of IEG’s USD 34 million budget in 2011 when the time devoted to a PPAR averaged six staff weeks (IEG 2011, 38). PPAR coverage differs across activities, depending on “novelty” and importance. For example, IEG kept PPAR coverage of structural adjustment programs at 100% in the 1980s while it reduced coverage of investment projects.

- 6.

Calculated from 1590 IBRD/IDA-funded projects with overall outcome ratings measured as “Satisfactory” or “Unsatisfactory.” For our estimation sample, it is 17.6%.

- 7.

PPAR is the report (also called a Project Performance Audit Report or just Project Audit Report in early IEG documents); PAR is the database name for its associated ratings.

- 8.

In a few cases, a second PPAR rating is available. To allow such variation, we take the project’s last PCR/EVM/ES entry as its ICR rating and the project’s first PPAR entry as its PPAR rating.

- 9.

Despite some selection based on ICR ratings, the overall share of projects initially rated satisfactory does not vary much between those projects that get reevaluated and others: ICR ratings average 72% satisfactory for projects with no subsequent PPAR versus 78% for projects with a subsequent PPAR. Starting in the mid-1980s, IEG began “group audits” for sequences of projects in the same sector in a given country and “cluster audits” of similar projects in several neighboring countries (Grasso et al. 2003, 48–49). Selection of projects for a PPAR is ultimately the decision of IEG division chiefs but with input from staff (Grasso et al. 2003, 49).

- 10.

This pattern is apparent in IEG (2010); Appendix B reports that only 12% of projects with an economic rate of return above 10% were rating “moderately unsatisfactory” or lower. Denizer et al. (2013) argue that World Bank procedures promote applying relatively uniform standards to goal setting and evaluation.

- 11.

The Vocational Training and Technological Development Project in Uruguay was approved in 1978 and completed in 1986. Its PCR (equivalent to an ICR) was issued in 1988 and the project was included with two subsequent Uruguayan education projects in a 2006 PPAR. The longest interval in our estimation sample is 12.75 years.

- 12.

Countries with ICRs (# ICRs in parentheses) but no PPARs as of 9/30/2013 are: Angola (15), Cape Verde (22), Sao Tome and Principe (13), Tonga (5), the Bahamas (5), Grenada (9), St. Kitts and Nevis (5), St. Vincent and the Grenadines (6), Turkmenistan (3), West Bank and Gaza (40), Kosovo (20), Namibia (2), Montenegro (5), South Sudan (1).

- 13.

The hazard model explores how the time until PPAR depends on institutional, country, and project characteristics. This is a form of a duration model that allows for censoring. Specifically, the model treats cases without a PPAR as not yet having a PPAR, since in principle a project could be audited at any point in the future. Estimation results are reported in terms of a hazard ratio relative to the baseline so that a ratio greater than one indicates a higher likelihood (“greater risk”) of a PPAR/shorter time until a PPAR; a ratio less than one indicates a lower likelihood of a PPAR/longer time until a PPAR. Hazard ratios have the advantage of not depending on values of the other variables (just as slope terms in a linear model do not depend on where you evaluate them).

- 14.

The hazard model sample includes all years with available data whereas the PPAR rating sample below excludes FY2002 (which proves to be an outlier in that setting perhaps due to the 9/11 attacks). Hazard model results are largely unchanged if we also exclude FY2002 here.

- 15.

Tourism data are sparse so we average across available years for each country, resulting in a purely cross-sectional variable. The specification also includes log population so that the tourism coefficient would be the same if we measured tourist arrivals per capita.

- 16.

We add one before taking logs; we disregard the few negative values reported by the OECD since this is defined as a gross measure.

- 17.

Results are similar if we use current year membership only. However, the three-year period has a few advantages. It allows for the delay between the decision to carry out a PPAR and the release of the PPAR. It also simplifies treatment of cases where the country held the WBEB seat for only part of the calendar year (since WBEB membership follows the World Bank’s fiscal year).

- 18.

The Weibull distribution is a generalization of the exponential distribution and is commonly used in hazard models because it is more flexible than the exponential and results in constant hazard ratios. We select logit (which estimates the probability of a PPAR by the end date) rather than probit because logit odds ratios can easily be compared to hazard ratios.

- 19.

Results comparable for Gompertz, loglogistic, and lognormal distributions. A likelihood ratio test rejects the shape assumption of the exponential model in favor of Weibull though results are again similar. Estimates are similar with gamma distribution but standard errors are larger and a few variables (notably June ICR) fail to reach statistical significance.

- 20.

However, if we omit GDP per capita in this multivariate model, the IDA hazard ratio becomes significantly greater than one. The two variables are strongly correlated as only low-income countries qualify for IDA’s concessional credits. (This may also explain why, in the specifications of Table 6.5 below, IDA is significant while log GDP PC is not).

- 21.

The impact of a single year is trivial but years in office range from 1 to 45 so there is a sizeable effect some cases. Because years in office might be related to conflict, we explored the impact of a conflict dummy derived from PRIO data. The magnitude of the Years in office hazard rate is unchanged and so is not driven by omitted information about conflict.

- 22.

Again, controlling for conflict does not change results.

- 23.

IEG states: “Each PPAR is subject to internal IEG peer review, Panel review, and management approval. Once cleared internally, the PPAR is commented on by the responsible Bank department. The PPAR is also sent to the borrower for review. IEG incorporates both Bank and borrower comments as appropriate, and the borrowers’ comments are attached to the document that is sent to the Bank’s Board of Executive Directors. After an assessment report has been sent to the Board, it is disclosed to the public.” (IEG 2015a, vi)

- 24.

We do not interact UNSC with Downgrade or Upgrade because, in combination, these are rare events, for example, only seven cases where a UNSC member has a downgrade. Looking at UNSC membership, timing is critical (since nonpermanent membership lasts only two years) whereas it is less critical when considering other geopolitical variables (bilateral aid, UN voting alignment, etc.) that vary less over time. This explains why results differ between UNSC@ICR and UNSC@PPAR while results for the other geopolitical variables do not depend on whether measured at the time of the ICR or the PPAR.

- 25.

We do not present ordered probit results because of the challenges involved in presenting useful marginal effects in this setting. However, the sign and significance of estimated coefficients for the ordered probit latent variable model match the linear model.

- 26.

Project characteristics include an IDA dummy and a Program Loan dummy. Country characteristics include GDP per capita, GDP growth rate, inflation, openness, the ratio of short-term debt to total debt, the average number of years of schooling, the combined Freedom House rating, and government years in office, all at approval. Sample size falls from 1500 observations (on 120 countries) in the parsimonious specifications to 1329 observations (on 93 countries) in the full specification. This is less than the 1371 observations in Table 6.5 because we exclude FY2002 PPARs. The full specification probit sample is slightly smaller still, at 1219 observations (on 69 countries) due to lack of variation in PPAR ratings (all Satisfactory or all Unsatisfactory) in some countries.

References

- Azevedo, João Pedro. 2011. wbopendata: Stata module to access World Bank databases, Statistical Software Components S457234, Boston College Department of Economics. http://ideas.repec.org/c/boc/bocode/s457234.html

- Beck, Thorsten, George Clarke, Alberto Groff, Philip Keefer, and Patrick Walsh. 2001. New tools in comparative political economy: The Database of Political Institutions. World Bank Economic Review 15:165–176.

Article Google Scholar

- Blum, Jürgen René. 2014. What factors predict how public sector projects perform? A review of the World Bank’s public sector management portfolio. World Bank Policy Research Working Paper 6798.

Google Scholar

- Bulman, David, Walter Kolkma, and Aart Kraay. 2017. Good countries or good projects? Comparing macro and micro correlates of World Bank and Asian Development Bank project performance. Review of International Organizations 12(3):335–363.

Article Google Scholar

- Buntaine, Mark, and Bradley C. Parks. 2013. When do environmentally-focused assistance projects achieve their objectives? Evidence from World Bank post-project evaluations. Global Environmental Politics 13(2):67–90.

Article Google Scholar

- Chauvet, Lisa, Paul Collier, and Marguerite Duponchel. 2010. What explains aid project success in post-conflict situations? World Bank Policy Research Working Paper 5418.

Google Scholar

- Chauvet, Lisa, Paul Collier, and Andreas Fuster. 2017. Supervision and Project Performance: A Principal-Agent Approach.〈hal-01516966〉.

Google Scholar

- Cruz, Cesi, and Philip Keefer. 2013. The organization of programmatic parties and the politics of bureaucratic reform. World Bank Policy Research Working Paper 6686.

Google Scholar

- Deininger, Klaus, Lyn Squire, and Swati Basu. 1998. Does economic analysis improve the quality of foreign assistance? World Bank Economic Review 12(3):385–418.

Article Google Scholar

- Denizer, Cevdet, Daniel Kaufmann, and Aart Kraay. 2013. Good countries or good projects? Macro and micro correlates of World Bank project performance. Journal of Development Economics 105:288–302.

Article Google Scholar

- Dollar, David, and Victoria Levin. 2005. Sowing and reaping: Institutional quality and project outcomes in developing countries. World Bank Policy Research Working Paper # 3524.

Google Scholar

- Dollar, David, and Jakob Svensson. 2000. What explains the success or failure of structural adjustment programmes? The Economic Journal 110(466):894–917.

Article Google Scholar

- Dreher, Axel, Jan-Egbert Sturm, and James Vreeland. 2009. Development aid and international politics: Does membership on the UN Security Council influence World Bank decisions? Journal of Development Economics 88: 1–18.

Article Google Scholar

- Dreher, Axel, Stephan Klasen, James Raymond Vreeland, and Eric Werker. 2013. The costs of favoritism: Is politically-driven aid less effective? Economic Development and Cultural Change 62(1):157–191.

Article Google Scholar

- Freedom House. 2012. Freedom in the World.

Google Scholar

- Geli, Patricia, Aart Kraay, and Hoveida Nobakht. 2014. Predicting World Bank project outcome ratings. World Bank Policy Research Working Paper 7001.

Google Scholar

- Girod, Desha M., and Jennifer Tobin. 2016. Take the money and run: The determinants of compliance with aid agreements. International Organization 70(1) 209–239.

Article Google Scholar

- Grasso, Patrick G., Sulaiman S. Wasty, Rachel V. Weaving (Eds). 2003. World Bank Operations Evaluation Department: The First 30 Years. Washington, DC: The World Bank.

Google Scholar

- Guillaumont, Patrick, and Rachid Laajaj. 2006. When instability increases the effectiveness of aid projects. World Bank Policy Research Working Paper # 4034.

Google Scholar

- IEG (World Bank Independent Evaluation Group). 2010. Cost-Benefit Analysis in World Bank Projects. Washington, DC: The World Bank.

Google Scholar

- IEG (World Bank Independent Evaluation Group). 2011. IEG Work Program and Budget (FY12) and Indicative Plan (FY13–14). Washington, DC: The World Bank.

Google Scholar

- IEG (World Bank Independent Evaluation Group). 2014. Independent Evaluation Group - World Bank Project Performance Ratings. http://ieg.worldbankgroup.org/ratings

- IEG (World Bank Independent Evaluation Group). 2015a. Project Performance Assessment Report. Brazil: First Programmatical Reform Loan for Environmental Sustainability. Report No.: 92270-BR.

Google Scholar

- IEG (World Bank Independent Evaluation Group). 2015b. World Bank Project Performance Ratings - Codebook. https://ieg.worldbankgroup.org/Data/reports/ieg-wb-project-performance-ratings-codebook_092015.pdf

- Isham, Jonathan, Daniel Kaufmann, and Lant Pritchett. 1997. Civil liberties, democracy, and the performance of government projects. World Bank Economic Review 11(2):219–242.

Article Google Scholar

- Isham, Jonathan, and Daniel Kaufmann. 1999. The forgotten rationale for policy reform: The productivity of investment projects. Quarterly Journal of Economics 114(1):149–184.

Article Google Scholar

- Kaufmann, Daniel, and Yan Wang. 1995. Macroeconomic policies and project performance in the social sectors: A model of human capital production and evidence from LDCs. World Development 23(5)751–765.

Article Google Scholar

- Kaja, Ashwin, and Eric Werker. 2010. Corporate governance at the World Bank and the dilemma of global governance. World Bank Economic Review 24(2):171–198.

Article Google Scholar

- Kersting, Erasmus, and Christopher Kilby. 2016. With a little help from my friends: Global electioneering and World Bank lending. Journal of Development Economics 121:153–165.

Article Google Scholar

- Kilby, Christopher. 2000. Supervision and performance: The case of World Bank projects. Journal of Development Economics 62(1):233–259.

Article Google Scholar

- Kilby, Christopher. 2009. The political economy of conditionality: an empirical analysis of World Bank loan disbursements. Journal of Development Economics 89(1):51–61.

Article Google Scholar

- Kilby, Christopher. 2013a. An empirical assessment of informal influence in the World Bank. Economic Development and Cultural Change 61(2):431–464.

Article Google Scholar

- Kilby, Christopher. 2013b. The political economy of project preparation: An empirical analysis of World Bank projects. Journal of Development Economics 105:211–225.

Article Google Scholar

- Kilby, Christopher. 2015. Assessing the impact of World Bank preparation on project outcomes. Journal of Development Economics 115:111–123.

Article Google Scholar

- Limodio, Nicola. 2011. The success of infrastructure projects in low income countries and the role of selectivity. World Bank Policy Research Working Paper # 5694.

Google Scholar

- Malesa, Thaddeus, and Peter Silarszky. 2005. Does World Bank effort matter for success of adjustment operations? In Stefan Koeberle, Harold Bedoya, Peter Silarsky, and Gero Verheyen (Eds.), Conditionality Revisited: Concepts, Experiences, and Lessons. (Washington: The World Bank). Chapter 13, pages 127–141.

Google Scholar

- Malik, Rabia, and Randall W. Stone. 2018. Corporate influence in World Bank lending. Journal of Politics 80(1):103–1118.

Article Google Scholar

- Michaelowa, Katharina, and Axel Borrmann. 2006. Evaluation bias and incentive structures in bi- and multilateral aid agencies. Review of Development Economics 10(2):313–329.

Article Google Scholar

- Moll, Peter, Patricia Geli, and Pablo Saavedra. 2015. Correlates of success in World Bank development policy lending. World Bank Policy Research Working Paper 7181.

Google Scholar

- Morrison, Kevin M. 2013. Membership no longer has its privileges: The declining informal influence of board members on IDA lending. Review of International Organizations 8(2):291–312.

Article Google Scholar

- OECD (Organization for Economic Cooperation and Development). 2015. Geographical distribution of financial flows: Flows to developing countries. OECD International Development Statistics (database). https://doi.org/10.1787/data-00566-en.

- Pohl, Gerhard, and Dubravko Mihaljek. 1992. Project evaluation and uncertainty in practice: A statistical analysis of rate-of-return divergences of 1,015 World Bank projects. The World Bank Economic Review 6(2):255–277.

Article Google Scholar

- Ralston, Laura. 2014. Success in difficult environments: A portfolio analysis of fragile and conflict-affected states. World Bank Policy Research Working Paper 7098.

Google Scholar

- Smets, Lodewijk, Stephen Knack, and Nadia Molenaers. 2013. Political ideology, quality at entry and the success of economic reform programs. Review of International Organizations 8(4):447–476.

Article Google Scholar

- Stone, Randall. 2008. The scope of IMF conditionality. International Organization 62:589–620.

Article Google Scholar

- Strezhnev, Anton, and Erik Voeten. 2012. United Nations General Assembly Voting Data, https://dataverse.harvard.edu/dataset.xhtml?persistentId=hdl:1902.1/12379.

- Sud, Inder, and Jane Olmstead-Rumsey. 2012. Development outcomes of World Bank projects: Real or illusory improvements. George Washington University Institute for Global and International Studies Working Paper #1.

Google Scholar

- United Nations. 2014. Countries Elected Members of the Security Council. http://www.un.org/en/sc/members/elected.asp Accessed 9/15/2014.

- USAID (United States Agency for International Development). 2014. U.S. overseas loans and grants: Obligations and loan authorizations, July 1, 1945–September 30, 2012 (Greenbook). https://explorer.usaid.gov/reports-greenbook.html Accessed 3/20/2014.

- U.S. State Department. 1984–2013. Voting Practices in the United Nations. GPO, Washington.

Google Scholar

- Winters, Matthew S. 2014. Targeting, accountability and capture in development projects. International Studies Quarterly 58(2):393–404.

Article Google Scholar

- World Bank. 2012a. Access to Information. Annual Report FY 2011. Moving Forward Transparency and Accountability. (Washington: The World Bank).

Google Scholar

- World Bank. 2012b. Projects database. http://go.worldbank.org/KPMUDAVVT0 Accessed 11/30/2012.

- World Bank. 2014. World Development Indicators. http://databank.worldbank.org/data/reports.aspx?source=world-development-indicators Accessed 10/14/2014.

Download references

Author information

Authors and Affiliations

- Villanova University, Villanova, PA, USA

Christopher Kilby

- University of Zurich, Zurich, Switzerland

Katharina Michaelowa

Editor information

Editors and Affiliations

- University of Wisconsin-La Crosse, La Crosse, WI, USA

Nabamita Dutta

- Mississippi State University, Mississippi, MS, USA

Claudia R. Williamson

Appendix

Table 6.8 Data sources

From: What Influences World Bank Project Evaluations?

| Beck et al. (2001): | Years in office |
| --- | --- |
| Freedom House (2012): | Freedom House |
| IEG (2014): | Outcome (ICR); ICR quality; log # WB projects; June ICR |
| Kaja and Werker (2010): | WBEB@ICR |
| OECD (2015): | log US Aid; log G7 Aid |
| Strezhnev and Voeten (2012); U.S. State Department (1984–2013): | US UN voting; G7 UN voting |
| United Nations (2014): | UNSC@ICR |
| USAID (2014): | US military aid |
| World Bank (2012b): | IDA; Program Loan; SIL; Regional dummies |
| Azevedo (2011); World Bank (2014): | log World Bank debt; log Project size; Tourism; log Population; log GDP PC; GDP growth; Inflation |

Table 6.9 Acronym list

From: What Influences World Bank Project Evaluations?

| DAC | Development Assistance Committee (also called Development Co-operation Directorate) of the Organization for Economic Cooperation and Development (OECD) |
| --- | --- |
| DGO | Director General, Operations |
| EAP | East Asia and Pacific |
| ECA | Europe and Central Asia |
| ED | Executive Director |
| ES | Evaluation Summary |
| EVM | Evaluation Memorandum |
| FY | Fiscal Year (July 1–June 30) |
| G7 | Group of 7 (Canada, France, Germany, Italy, Japan, United Kingdom, United States) |
| GDP | Gross Domestic Product |
| IBRD | International Bank for Reconstruction and Development |
| ICR | Implementation Completion Report or Implementation Completion and Results Report |
| IDA | International Development Association |
| IEG | Independent Evaluation Group |
| LAC | Latin America and the Caribbean |
| MENA | Middle East and North Africa |
| OED | Operations Evaluation Department |
| PAR | Project Assessment Report |
| PCM | Project Cancellation Memorandum |
| PCN | Project Cancellation Note |
| PCR | Project Completion Report |
| PPAR | Project Performance Audit Report |
| SA | South Asia |
| SIL | Specific Investment Loan |
| SSA | Sub-Saharan Africa |
| UN | United Nations |
| UNSC | United Nations Security Council |
| USD | US Dollar |
| WBEB | World Bank Executive Board |

Political ideology, quality at entry and the success of economic reform programs

- Published: 06 March 2013

- Volume 8, pages 447–476, (2013)

- Cite this article

Top of Form

Save article

Bottom of Form

View saved research

The Review of International OrganizationsAims and scopeSubmit manuscript

- Lodewijk Smets,

- Stephen Knack &

- Nadia Molenaers

- 782 Accesses

- 49 Citations

- 4 Altmetric

- Explore all metrics

Abstract

This study investigates how government ideology matters for the success of World Bank economic policy loans, which typically support market-liberalizing reforms. A simple model predicts that World Bank staff will invest more effort in designing an economic policy loan when faced with a left-wing government. Empirically, estimates from a Heckman selection model show that the quality at entry of an economic policy loan is significantly higher for governments with a left-wing party orientation. This result is robust to changes in the sample, alternative measures of ideology, different estimation techniques and the inclusion of additional control variables. Next, robust findings from estimating a recursive triangular system of equations indicate that leftist governments comply more fully with loan agreements. Results also suggest that World Bank resources are more productive—in terms of reform success—in the design of policy operations than in their supervision. Anecdotal evidence from several country cases is consistent with the finding that left-wing governments receive higher quality loans.

This is a preview of subscription content, log in via an institution  to check access.

Access this article

Log in via an institution

Subscribe and save

Springer+

from €37.37 /Month

- Starting from 10 chapters or articles per month

- Access and download chapters and articles from more than 300k books and 2,500 journals

- Cancel anytime

View plans

Buy Now

Top of Form

Buy article PDF 39,95 €

Bottom of Form

Price includes VAT (Australia)

Instant access to the full article PDF.

Institutional subscriptions

Similar content being viewed by others

Power, ideas, and World Bank conditionality

Article 31 May 2021

Towards a wellbeing economy: Portuguese policymakers’ perspectives

Article 25 November 2025

Party governments, clientelistic reforms, and varying levels of political constraints

Article 04 August 2016

Explore related subjects

Discover the latest articles, books and news in related subjects, suggested using machine learning.

- Comparative Politics

- Economic Policy

- Political Psychology

- Political Theory

- Public Choice and Political Economy

- Self-serving bias

- Public Administration Reform and Governance

Notes

- Interviews were conducted in August 2011 at the World Bank Headquarters in Washington D.C.

- A number of interesting studies in this respect are Wittman (1983), Alesina (1988), Glazer and Grofman (1989), Alesina and Cukierman (1990), Roemer (1997, 1999) and Terai (2006). Both Drazen (2000) and Persson and Tabellini (2000) provide an extensive overview on the political economy of economic reform.

- A partial listing includes Beck (1982), Bjørnskov (2005, 2008), Bortolotti and Pinotti (2008), Dutt and Mitra (2005, 2006), Frey and Schneider (1978), Hibbs (1977), Pitlik (2007), and Potrafke (2010).

- Policy decisions are not influenced solely by ideology, of course; staying in office and other considerations also matter. See for example Persson and Tabellini (2000).

- According to the theory of cognitive dissonance, a person who behaves in a way contrary to his beliefs is motivated by resulting discomfort or anxiety to reduce this “cognitive dissonance,” e.g., by changing his beliefs. Cognitive dissonance theory has been widely applied in social science research. For applications in the field of economics, see among others Akerlof and Dickens (1982) and Gilad et al. (1987). Hirschman (1965) and James and Gutkind (1985) have applied it to claim that the coercive nature of conditional aid hinders reform.

- For multi-tranche operations a Tranche Release Document is prepared on the basis of which the decision is taken to release subsequent tranches.

- A DPL task team leader interviewed for this study suggested that matching World Bank staff with governments might not be random; for example, more capable staff members might be assigned to work with more ‘difficult’ governments. On the other hand, to the extent higher-quality staff have more leverage in choosing their assignments, they might opt to work with less difficult governments, where their advice is more welcome. Data limitations prevent us from measuring staff quality. Denizer et al. (2011) control for the impact of task leader fixed effects on project success, but our sample of policy loans is too small to implement this approach.

- In our model we assume a positive mapping from effort to program quality, which in turn positively affects the expected returns of a loan. However, it is conceivable that World Bank effort might reduce quality at entry—by, e.g., ignoring local conditions—as to accomodate to unfriendly governments. Yet, the cases presented in Section 5 do not seem consistent with this hypothesis and rather indicate a positive mapping between effort and program quality. Furthermore, the effort put in does not merely serve to design a program the recipient government will agree to, but also Bank management and the Board of Directors, who demand at least some minimum expected returns.

- The salary incentive can be generalized to non-pecuniary sources of utility, such as the utility World Bank staff receive from continued policy dialogue with high-level government officials. Arguably, the policy dialogue with a left-wing government would be damaged more by a failed policy reform program, so staff have an added incentive to design a higher-quality loan.

- This assumption holds if .

- A case in point is post-apartheid South Africa, where the COSATU-backed ANC government for a long time disagreed with the World Bank’s lending proposals.

- The Country Policy and Institutional Assessments (CPIA) are subjective ratings of 16 indicators updated annually by World Bank staff, and used for allocating IDA loans.

- We have also included party orientation as a selection variable, yet it did not turn out to influence receipt of DPL.

- The IEG uses the Bank’s Implementation Completion and Results Reports (ICRs) as a starting point to evaluate the different stages of a reform program. The validity of the IEG measures might be questioned (see, e.g., Dreher et al. 2010). However, Kilby (2000, pp. 239–247), Dollar and Svensson (2000, pp. 897–899) and Denizer et al. (2011, pp. 7–10) persuasively defend the IEG ratings as valid measures of program success. They provide the following arguments (among others): (i) the IEG is independent of the Bank’s senior management; (ii) the outcome variables are highly correlated with improvements in observed economic performance; (iii) IEG ratings do not significantly differ from the more in-depth and detailed “Project Performance Audit Reports.” Unfortunately, the latter ratings are available only for a very limited sample of DPLs. While there surely is still remaining measurement error, there is no reason to believe the IEG ratings are biased, particularly with respect to government ideology. The latter view is supported by interviews of experienced IEG staff members. Nevertheless, to control for a potential political bias of World Bank ratings, we have included the overall CPIA rating in one of the robustness tests. That is, if IEG staff are biased then regular Bank staff—who generate the CPIA ratings—should produce similar biases.

- The Database of Political Institutions was constructed in 2001 and initially covered 177 countries for the period 1975–1995. The database is periodically updated: the most recent version dating to 2010 contains information from 1975 through 2009.

- Following Dreher and Sturm (2012), we consider the G-7 as a country group. The variable reflects the average G-7 vote by weighing each G-7 countries’ vote with its quota in the IMF.

- Given that our sample contains a limited number of countries and a limited number of observations per country, we have opted to include regional fixed effects instead of country fixed effects.

- The model’s predictions mainly apply to quality at entry and not to the other stages of the reform process. Extending the model to those other stages is beyond the scope of this paper but may be an interesting area for further research.

- For the triangular model to be fully recursive, we assume a diagonal variance covariance matrix . It is conceivable that this assumption is violated as an omitted variable may simultaneously affect the left-hand side variables. However, a likelihood ratio test of uncorrelated errors yields a  statistic of 2.87 with corresponding p-value of 0.4123. Triangular systems also assume a certain ordering of endogenous variabes in a sense that the ith equation may contain endogenous variables whose position is lower than i (Lahiri and Schmidt 1978). As the World Bank formulates monitoring and evaluation arrangements in the preparation stage of the program, they signal their supervision intentions before the start of the program. Next, part of the supervision effort includes an evaluative review to identify problems during implementation and recommendations to resolve them. For these reasons we include Bank supervision on the right hand side of the second (compliance) equation. On the other hand, it is standard operating procedure to supervise loan agreements irrespective of the extent of borrower compliance. However, Dollar and Svensson (2000) assume that exogenous shocks that reduce the probability of compliance also influence the allocation of World Bank resources (for supervision). As such they claim that donor variables are endogenous to DPL success. Malesa and Silarszky (2005) statistically test this reasoning but fail to find any evidence that supervision costs (and other donor variables) are endogenous to the probability of success. They explain this by the fact that resources for supervision are budgeted in advance. That is why we have opted to exclude compliance from the first equation.

- See Besley and Case (2003) for a detailed literature review on how political factors affect (economic) policy choice.

- Dreher et al. (2009a) find that market-liberalizing policy reforms are inversely related to the chief executive’s time in office.

- Additionally, we have tested our model by including a set of dummies reflecting the sectoral target of policy loans and find that results change very little. Regression results are not tabulated but are available upon request.

- However, an omitted variable such as staff capacity may well affect quality at entry and supervision in the same way. Yet, it is not uncommon in World Bank practice to have various staff teams working on the different stages of one DPL.

- The authors identify three conditions for such a policy switch to occur: firstly, the desirability of the policy switch should be considerable and relatively rare. Second, policy reversals are more prone to occur when voters are uncertain about the government’s preferences. Finally, the outcomes of the policies under consideration take place in the future. However, Cowen and Sutter (1998) have shown that similar policy reversals also hold under less stringent conditions.

- The results of the model with time fixed effects are line with the base model, but are not included due to space considerations.

- In three other cases, interviews suggested that ideology was less salient. The four cases discussed, and the 7 selected in total, are not necessarily representative of all DPLs. A form of “convenience sampling” was employed, in which the authors selected task team leaders who were judged most likely to respond favorably to interview requests. Whether representative or not, the cases are illustrative of the main arguments and intuition behind the model.

- Note that at that time FRELIMO already discarded its radical Marxist-Leninist ideology—-yet still situated firmly on the left—which allowed the World Bank the opportunity to discuss market reforms. In terms of the model, it was no longer the case that .

- During the interviews a team task manager mentioned that attitude change was also crucial in successfully supporting the economic reform programs in Vietnam.

- Within the MMD there were outspoken differences concerning the impact of market reforms. President Levy Mwanawasa opposed privatization arguing that market policies “had brought untold suffering to the workers” while his Finance Minister Emmanuel Kasonde maintained that it was inevitable to redress the situation where state-owned enterprises continue to depend on the state for subventions. Following these differences over privatization, Emmanuel Kasonde was relieved of his ministerial position by the Mwanawasa Government (World Bank 2004).

- In terms of the model: a government with low reservation utility for accepting the reform program.

References

- Akerlof, G.A., & Dickens, W.T. (1982). The economic consequences of cognitive dissonance. The American Economic Review, 72(3), 307–319.

Google Scholar

- Alesina, A. (1988). Credibility and policy convergence in a two-party system with rational voters. The American Economic Review, 78(4), 796–805.

Google Scholar

- Alesina, A., & Cukierman, A. (1990). The politics of ambiguity. The Quarterly Journal of Economics, 105(4), 829–850.

Article Google Scholar

- Andersen, T.B., Hansen, H., Markussen, H. (2006). US politics and World Bank IDA-lending. The Journal of Development Studies, 42(5), 772–794.

Article Google Scholar

- Beck, N. (1982). Parties, administrations, and American macroeconomic outcomes. The American Political Science Review, 76(1), 83–93.

Article Google Scholar

- Beck, T., Clarke, G., Groff, A., Keefer, P., Walsh, P. (2001). New tools in comparative political economy: the database of political institutions. The World Bank Economic Review, 15(1), 165–176. http://go.worldbank.org/2EAGGLRZ40.

Article Google Scholar

- Besley, T., & Case, A. (2003). Political institutions and policy choices: evidence from the United States. Journal of Economic Literature, 41(1), 7–73.

Article Google Scholar

- Besley, T., Montalvo, J.G., Reynal-Querol, M. (2011). Do educated leaders matter? Economic Journal, 121(554), F205–F227.

Article Google Scholar

- Bienen, H., & Van De Walle, N. (1989). Time and power in Africa. The American Political Science Review, 83(1), 19–34.

Article Google Scholar

- Bjørnskov, C. (2005). Does political ideology affect economic growth? Public Choice, 123, 133–146.

Article Google Scholar

- Bjørnskov, C. (2008). The growth-inequality association: government ideology matters. Journal of Development Economics, 87(2), 300–308.

Article Google Scholar

- Bortolotti, B., & Pinotti, P. (2008). Delayed privatization. Public Choice, 136(3), 331–351.

Article Google Scholar

- Bueno de Mesquita, B., Morrow, J.D., Siverson, R.M., Smith, A. (2002). Political institutions, policy choice and the survival of leaders. British Journal of Political Science, 32(4), 559–590.

Article Google Scholar

- Chai, S.-K. (1998). Endogenous ideology formation and economic policy in former colonies. Economic Development and Cultural Change, 46(2), 263–90.

Article Google Scholar

- Chauvet, L., Collier, P., Fuster, A. (2006). Supervision and project performance: A principal-agent approach. University of Oxford: Centre for the Study of African Economies.

Google Scholar

- Cowen, T., & Sutter, D. (1998). Why only Nixon could go to China. Public Choice, 97(4), 605–615.

Article Google Scholar

- Cukierman, A., & Tommasi, M. (1998). When does it take a Nixon to go to China? American Economic Review, 88, 180–197.

Google Scholar

- Denizer, C., Kaufmann, D., Kraay, A. (2011). Good countries or good projects? Macro and micro correlates of World Bank project performance. Policy Research Working Paper Series 5646, The World Bank.

- Dijkstra, G.A. (2002). The effectiveness of policy conditionality: eight countries experiences. Development and Change, 33(2), 307–334.

Article Google Scholar

- Dollar, D., & Svensson, J. (2000). What explains the success or failure of structural adjustment programmes?The Economic Journal, 110, 894–917.

Article Google Scholar

- Drazen, A. (2000). Political economy in macroeconomics. New Jersey: Princeton University Press.

Google Scholar

- Dreher, A., Klasen, S., Vreeland, J.R.,Werker, E. (2010). The costs of favoritism: is politically-driven aid less effective? CESifo Working Paper Series 2993, CESifo Group Munich.

- Dreher, A., Lamla, M.J., Lein, S.M., Somogyi, F. (2009a). The impact of political leaders’ profession and education on reforms. Journal of Comparative Economics, 37(1), 169–193.

Article Google Scholar

- Dreher, A., & Sturm, J.-E. (2012). Do the IMF and the World Bank influence voting in the UN General Assembly? Public Choice, 151(1), 363–397.

Article Google Scholar

- Dreher, A., Sturm, J.-E., Vreeland, J.R. (2009b). Development aid and international politics: does membership on the UN security council influence World Bank decisions?Journal of Development Economics, 88(1), 1–18.

Article Google Scholar

- Dutt, P., & Mitra, D. (2005). Political ideology and endogenous trade policy: an empirical investigation. The Review of Economics and Statistics, 87(1), 59–72.

Article Google Scholar

- Dutt, P., & Mitra, D. (2006). Labor versus capital in trade-policy: the role of ideology and inequality. Journal of International Economics, 69(2), 310–320.

Article Google Scholar

- Frey, B.S., & Schneider, F. (1978). An empirical study of politico-economic interaction in the United States. The Review of Economics and Statistics, 60(2), 174–183.

Article Google Scholar

- Gilad, B., Kaish, S., Loeb, P.D. (1987). Cognitive dissonance and utility maximization: a general framework. Journal of Economic Behavior and Organization, 8(1), 61–73.

Article Google Scholar

- Glazer, A., & Grofman, B. (1989). Why representatives are ideologists though voters are not. Public Choice, 61(1), 29–39.

Article Google Scholar

- Haggard, S., & Webb, S. (Eds.) (1994). Voting for reform: Democracy, political liberalisation, and economic adjustment. Oxford: Oxford University Press.

Google Scholar

- Heckman, J.J. (1979). Sample selection bias as a specification error. Econometrica, 47(1), 153–161.

Article Google Scholar

- Hibbs, D.A. (1977). Political parties and macroeconomic policy. The American Political Science Review, 71(4), 1467–1487.

Article Google Scholar

- Hirschman, A.O. (1965). Obstacles to development: a classification and a quasi-vanishing act. Economic Development and Cultural Change, 13(4), 385.

Article Google Scholar

- IEG. (2006). . Washington, D.C.: World Bank.

Google Scholar

- James, J., & Gutkind, E. (1985). Attitude change revisited: cognitive dissonance theory and development policy. World Development, 13(10–11), 1139–1149.

Article Google Scholar

- Jones, B.F., & Olken, B.A. (2005). Do leaders matter? National leadership and growth since World War II. The Quarterly Journal of Economics, 120(3), 835–864.

Google Scholar

- Kapur, D., Lewis, J.P., Webb, R. (1997). The World Bank: Its first half century. Volume 1. History. Washington, D.C.: Brookings Institution Press.

Google Scholar

- Kilby, C. (2000). Supervision and performance: the case of World Bank projects. Journal of Development Economics, 62(1), 233–259.

Article Google Scholar

- Kilby, C. (2009). The political economy of conditionality: an empirical analysis of World Bank loan disbursements. Journal of Development Economics, 89(1), 51–61.

Article Google Scholar

- Kilby, C. (2011). The political economy of project preparation: An empirical analysis of world bank projects. Villanova School of Business Department of Economics and Statistics Working Paper Series 14, Villanova School of Business Department of Economics and Statistics.

- Killick, T. (1997). Principals, agents and the failings of conditionality. Journal of International Development, 9(4), 483–495.

Article Google Scholar

- Knack, S. (2012). When do donors trust recipient country systems? Policy Research Working Paper Series 6019, The World Bank.

- Krueger, A.O. (1993). Political economy of policy reform in developing countries. Cambridge, MA and London: The MIT Press.

Google Scholar

- Lahiri, K., & Schmidt, P. (1978). On the estimation of triangular structural systems. Econometrica, 46(5), 1217–21.

Article Google Scholar

- Malesa, T., & Silarszky, P. (2005). Does World Bank Effort matter for success of adjustment operations? Conditionality revisited: Concepts, experiences, and lessons (pp. 127–141). Washington, D.C.: World Bank.

Google Scholar

- Meseguer, C. (2006). Learning and economic policy choices. European Journal of Political Economy, 22(1), 156–178.

Article Google Scholar

- Mosley, P., Harrigan, J., Toye, J. (1991). Aid and power: The World Bank and policy-based lending Volume 1. Analysis and policy proposals. London and New York: Routledge.

Google Scholar

- Murshed, S.M. (2009). On the non-contractual nature of donor-recipient interaction in development assistance. Review of Development Economics, 13(s1), 416–428.

Article Google Scholar

- Navia, P., & Velasco, A. (2003). The politics of second-generation reforms. In P.-P. Kuczynski, & J. Williamson (Eds.) After the Washington consensus: Restarting growth and reform in Latin America. Institute for International Economics.

- Noorbakhsh, F., & Paloni, A. (2007). Learning from structural adjustment: why selectivity may not be the key to successful programmes in Africa. Journal of International Development, 19(7), 927– 948.

Article Google Scholar

- Persson, T., & Tabellini, G. (2000). Political economics, explaining economic policy. Cambridge, MA: The MIT Press.

Google Scholar

- Pitlik, H. (2007). A race to liberalization? Diffusion of economic policy reform among OECD-economies. Public Choice, 132(1), 159–178.

Article Google Scholar

- Potrafke, N. (2010). Does government ideology influence deregulation of product markets? Empirical evidence from OECD countries. Public Choice, 143(1), 135–155.

Article Google Scholar

- Ranis, G., & Mahmood, S.A. (1992). The political economy of development policy change. Cambridge, MA and Oxford: Basil Blackwell.

Google Scholar

- Rodrik, D. (2006). Goodbye Washington consensus, hello Washington confusion? Journal of Economic Literature, 44(4), 973–987.

Article Google Scholar

- Roemer, J.E. (1997). Politicaleconomic equilibrium when parties represent constituents: the unidimensional case. Social Choice and Welfare, 14, 479–502.

Article Google Scholar

- Roemer, J.E. (1999). The democratic political economy of progressive income taxation. Econometrica, 67(1), 1–19.

Article Google Scholar

- Shirk, D.A. (2004). Mexico’s new politics: the PAN and democratic change. Lynne Riener.

- Stromberg, D. (2007). Natural disasters, economic development, and humanitarian aid. Journal of Economic Perspectives, 21(3), 199–222.

Article Google Scholar

- Svensson, J. (2000). When is foreign aid policy credible? Aid dependence and conditionality. Journal of Development Economics, 61(1), 61–84.

Article Google Scholar

- Svensson, J. (2003). Why conditional aid does not work and what can be done about it? Journal of Development Economics, 70(2), 381–402.

Article Google Scholar

- Terai, K. (2006). Parties with policy preferences and uncertainty over voter behavior. Social Choice and Welfare, 27, 155–172.

Article Google Scholar

- Wane, W. (2004). The quality of foreign aid: Country selectivity or donors incentives? Policy Research Working Paper Series 3325, The World Bank.

- Williamson, J. (1994). The political economy of policy reform. No. 68 in Peterson Institute Press: All Books. Peterson Institute for International Economics.

- Wittman, D. (1983). Candidate motivation: a synthesis of alternative theories. The American Political Science Review, 77(1), 142–157.

Article Google Scholar

- World Bank. (2002). Mexico country economic memorandum: Challenges and prospects for tax reform. Washington, D.C.: World Bank.

Google Scholar

- World Bank. (2004). Zambia country economic memorandum: Policies for growth and diversification. Washington, D.C.: World Bank.

Google Scholar

- World Bank. (2005). Mozambique country economic memorandum: Sustaining growth and reducing poverty. Washington, D.C.: World Bank.

Google Scholar

Download references

Acknowledgements

We would like to thank the DPL team task leaders for making time available for the interviews, Peter Moll, Adam Wagstaff and Bruno De Borger for valuable comments, the editor of this journal and two anonymous referees for useful comments and suggestions, Vincenzo Verardi for helpful conversations, Christian Bjørnskov for sharing his data and Tim De Vaan and René Vandendries for providing insight in the IEG ratings. The authors are solely responsible for any remaining errors. Lodewijk Smets is also indebted to the Institute of Development Policy and Management (IOB) for providing a research grant.

Author information

Authors and Affiliations

- Institute of Development Policy and Management, University of Antwerp, Antwerpen, Belgium

Lodewijk Smets & Nadia Molenaers

- World Bank, Washington, DC, USA

Stephen Knack

Corresponding author

Correspondence to Lodewijk Smets.

Electronic Supplementary Material

Below is the link to the electronic supplementary material.

(ZIP 3.20 MB)

Appendix

Table 4 Triangular system, reduced sample

From: Political ideology, quality at entry and the success of economic reform programs

| Equation 1: Bank supervision |  |  | Equation 2 : Borrower compliance |  |  | Equation 3 : Outcome |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Variable | Coefficient | (Std. err.) | Variable | Coefficient | (Std. err.) | Variable | Coefficient | (Std. err.) |
| Quality at entry | 0.441*** | (0.108) | Bank supervision | 0.372*** | (0.142) | Bank supervision | 0.235** | (0.118) |
| Left | 0.108 | (0.289) | Quality at entry | 0.309*** | (0.115) | Borrower compliance | 0.239** | (0.097) |
| Growth t+1 | 0.015 | (0.035) | Left | 0.280 | (0.245) | Quality at entry | 0.346*** | (0.114) |
| Year | 0.008 | (0.028) | Growth t+1 | 0.069** | (0.028) | Left | 0.007 | (0.177) |
| Log of loan amount | −0.063 | (0.129) | Year | −0.024 | (0.026) | Growth t+1 | 0.072*** | (0.026) |
| Democratic regime | 0.113 | (0.381) | Log of loan amount | −0.129 | (0.149) | Year | −0.075*** | (0.020) |
| Incumbent tenure | 0.042 | (0.031) | Democratic regime | −0.106 | (0.488) | Log of loan amount | −0.209 | (0.128) |
| Log of GDP per capita (PPP) | −0.102 | (0.220) | Incumbent tenure | 0.001 | (0.035) | Democratic regime | 0.121 | (0.215) |
| Log of population | 0.025 | (0.137) | Log of GDP per capita (PPP) | 0.374 | (0.265) | Incumbent tenure | −0.014 | (0.018) |
| Voting in line with G7 t−1 | −1.353* | (0.767) | Log of population | 0.175 | (0.115) | Log of GDP per capita (PPP) | 0.510** | (0.219) |
| Nonselection hazard | −0.727 | (0.768) | Voting in line with G7 t−1 | −0.795 | (0.901) | Log of population | 0.088 | (0.095) |
| Regional fixed effects | yes | – | Nonselection hazard | −1.088 | (0.824) | Voting in line with G7 t−1 | −0.326 | (0.515) |
|  |  |  | Regional fixed effects | yes | – | Nonselection hazard | −1.678** | (0.699) |
|  |  |  |  |  |  | regional fixed effects | yes | – |

Table 5 Triangular system, expanded sample

From: Political ideology, quality at entry and the success of economic reform programs

| Equation 1: Bank supervision |  |  | Equation 2: Borrower compliance |  |  | Equation 3: Outcome |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Variable | Coefficient | (Std. err.) | Variable | Coefficient | (Std. err.) | Variable | Coefficient | (Std. err.) |
| Quality at entry | 0.423*** | (0.069) | Bank supervision | 0.305** | (0.119) | Bank supervision | 0.166** | (0.071) |
| Left | 0.113 | (0.225) | Quality at entry | 0.353*** | (0.086) | Borrower compliance | 0.338*** | (0.074) |
| Growth t+1 | 0.029 | (0.024) | Left | 0.366** | (0.175) | Quality at entry | 0.343*** | (0.076) |
| Year | −0.006 | (0.018) | Growth t+1 | 0.032 | (0.024) | Left | −0.033 | (0.131) |
| Log of loan amount | −0.067 | (0.098) | Year | −0.010 | (0.023) | Growth t+1 | 0.042** | (0.016) |
| Democratic regime | 0.134 | (0.274) | Log of loan amount | −0.188* | (0.114) | Year | −0.045*** | (0.010) |
| Incumbent tenure | 0.037* | (0.022) | Democratic regime | −0.161 | (0.314) | Log of loan amount | −0.145 | (0.097) |
| Log of GDP per capita (PPP) | −0.054 | (0.187) | Incumbent tenure | 0.015 | (0.026) | Democratic regime | 0.165 | (0.189) |
| Log of population | 0.113 | (0.121) | Log of GDP per capita (PPP) | −0.193 | (0.176) | Incumbent tenure | −0.009 | (0.016) |
| Voting in line with G7 t−1 | −0.578 | (0.654) | Log of population | 0.154 | (0.117) | Log of GDP per capita (PPP) | 0.067 | (0.153) |
| Nonselection hazard | 0.060 | (0.400) | Voting in line with G7 t−1 | 0.180 | (0.594) | Log of population | 0.022 | (0.082) |
| Regional fixed effects | yes | – | Nonselection hazard | −0.482 | (0.498) | Voting in line with G7 t−1 | −0.279 | (0.385) |
|  |  |  | Regional fixed effects | yes | – | Nonselection hazard | −0.598* | (0.306) |
|  |  |  |  |  |  | Regional fixed effects | yes | – |

- N 191

- Log-likelihood −3487.396

- Significance levels: *10 %; **5 %; ***1 %; no intercept reported

Table 7 Triangular system, 3-point categorical variable

From: Political ideology, quality at entry and the success of economic reform programs

| Equation 1: Bank supervision |  |  | Equation 2: Borrower compliance |  |  | Equation 3: Outcome |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Variable | Coefficient | (Std. err.) | Variable | Coefficient | (Std. err.) | Variable | Coefficient | (Std. err.) |
| Quality at entry | 0.512*** | (0.096) | Bank supervision | 0.243* | (0.127) | Bank supervision | 0.143 | (0.093) |
| Ideology | −0.048 | (0.139) | Quality at entry | 0.360*** | (0.104) | Borrower compliance | 0.342*** | (0.089) |
| Growth t+1 | 0.020 | (0.028) | Ideology | 0.219** | (0.103) | Quality at entry | 0.333*** | (0.102) |
| Year | −0.003 | (0.022) | Growth t+1 | 0.036 | (0.027) | Ideology | −0.047 | (0.088) |
| Log of loan amount | −0.040 | (0.094) | Year | −0.009 | (0.024) | Growth t+1 | 0.044** | (0.019) |
| Democratic regime | −0.050 | (0.283) | Log of loan amount | −0.112 | (0.108) | Year | −0.042*** | (0.013) |
| Incumbent tenure | 0.033 | (0.024) | Democratic regime | −0.221 | (0.345) | Log of loan amount | −0.194 | (0.129) |
| Log of GDP per capita (PPP) | −0.004 | (0.195) | Incumbent tenure | 0.023 | (0.025) | Democratic regime | 0.225 | (0.234) |
| Log of population | 0.092 | (0.116) | Log of GDP per capita (PPP) | −0.023 | (0.188) | Incumbent tenure | 0.001 | (0.018) |
| Voting in line with G7 | −0.569 | (0.709) | Log of population | 0.101 | (0.105) | Log of GDP per capita (PPP) | 0.078 | (0.176) |
| Nonselection hazard | 0.044 | (0.423) | Voting in line with G7 | −0.225 | (0.637) | Log of population | 0.061 | (0.104) |
| Regional fixed effects | yes | – | Nonselection hazard | −0.688 | (0.505) | Voting in line with G7 | −0.220 | (0.392) |
|  |  |  | Regional fixed effects | yes | – | Nonselection hazard | −0.819* | (0.448) |
|  |  |  |  |  |  | Regional fixed effects | yes | – |

- N 161

- Log-likelihood −2997.979

- Significance levels: *10 %; **5 %; ***1 %; no intercept reported

Table 8 Triangular system, binary LHS variables

From: Political ideology, quality at entry and the success of economic reform programs

| Equation 1: Bank supervision (dummy) |  |  | Equation 2: Borrower compliance (dummy) |  |  | Equation 3 : Outcome (dummy) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Variable | Coefficient | (Std. err.) | Variable | Coefficient | (Std. err.) | Variable | Coefficient | (Std. err.) |
| Dummy bankquality | 0.442*** | (0.089) | Dummy supervision | 0.140 | (0.126) | Dummy supervision | 0.311*** | (0.114) |
| Left | 0.033 | (0.068) | Dummy bankquality | 0.386*** | (0.098) | Dummy compliance | 0.271** | (0.109) |
| Growth t+1 | 0.006 | (0.007) | Left | 0.074 | (0.049) | Dummy bankquality | 0.184* | (0.100) |
| Year | 0.004 | (0.007) | Growth t+1 | 0.010 | (0.008) | Left | 0.011 | (0.046) |
| Log of loan amount | −0.025 | (0.028) | Year | 0.002 | (0.007) | Growth t+1 | 0.010* | (0.005) |
| Democratic regime | 0.079 | (0.077) | Log of loan amount | −0.020 | (0.033) | Year | −0.009* | (0.005) |
| Incumbent tenure | 0.016*** | (0.006) | Democratic regime | −0.125 | (0.103) | Log of loan amount | −0.034 | (0.046) |
| Log of GDP per capita (PPP) | −0.026 | (0.049) | Incumbent tenure | 0.005 | (0.007) | Democratic regime | 0.006 | (0.093) |
| Log of population | 0.042 | (0.032) | Log of GDP per capita (PPP) | −0.044 | (0.059) | Incumbent tenure | −0.002 | (0.006) |
| Voting in line with G7 t-1 | −0.182 | (0.204) | Log of population | 0.013 | (0.034) | Log of GDP per capita (PPP) | −0.066 | (0.050) |
| Nonselection hazard | 0.050 | (0.122) | Voting in line with G7 t-1 | −0.074 | (0.200) | Log of population | −0.003 | (0.034) |
| Regional fixed effects | yes | – | Nonselection hazard | −0.193 | (0.160) | Voting in line with G7 t-1 | 0.042 | (0.152) |
|  |  |  | regional fixed effects | yes | – | Nonselection hazard | −0.303** | (0.143) |
|  |  |  |  |  |  | Regional fixed effects | yes | – |

- N 161

- Log-likelihood −2144.738

- Significance levels: *10 %; **5 %; ***1 %; no intercept reported

Table 9 Triangular system, additional covariates

From: Political ideology, quality at entry and the success of economic reform programs

| Equation 1: Bank supervision |  |  | Equation 2: Borrower compliance |  |  | Equation 3: Outcome |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Variable | Coefficient | (Std. err.) | Variable | Coefficient | (Std. err.) | Variable | Coefficient | (Std. err.) |
| Quality at entry | 0.459*** | (0.067) | Bank supervision | 0.171* | (0.092) | Bank supervision | 0.148** | (0.069) |
| Left | −0.016 | (0.190) | Quality at entry | 0.375*** | (0.086) | Borrower compliance | 0.323*** | (0.061) |
| Growth t+1 | 0.041* | (0.022) | Left | 0.317 | (0.212) | Quality at entry | 0.365*** | (0.068) |
| Year | 0.012 | (0.018) | Growth t+1 | 0.055** | (0.025) | Left | −0.147 | (0.159) |
| Log of loan amount | −0.119 | (0.150) | Year | −0.012 | (0.020) | Growth t+1 | 0.052*** | (0.019) |
| Democratic regime | 0.203 | (0.309) | Log of loan amount | −0.254 | (0.167) | Year | −0.033** | (0.015) |
| Incumbent tenure | 0.044* | (0.024) | Democratic regime | 0.133 | (0.344) | Log of loan amount | −0.226* | (0.125) |
| Log of GDP per capita (PPP) | 0.154 | (0.238) | Incumbent tenure | 0.042 | (0.027) | Democratic regime | 0.184 | (0.257) |
| Log of population | 0.138 | (0.122) | Log of GDP per capita (PPP) | 0.303 | (0.266) | Incumbent tenure | −0.001 | (0.020) |
| Voting in line with G7 t-1 | −0.885 | (0.580) | Log of population | 0.238* | (0.137) | Log of GDP per capita (PPP) | 0.307 | (0.199) |
| Nonselection hazard | −0.228 | (0.516) | Voting in line with G7 t-1 | 0.022 | (0.652) | Log of population | 0.077 | (0.103) |
| CPIA score | −0.360* | (0.214) | Nonselection hazard | −0.034 | (0.575) | Voting in line with G7 t-1 | −0.446 | (0.485) |
| Current account balance (% of GDP) | −0.003 | (0.017) | CPIA score | 0.155 | (0.241) | Nonselection hazard | −0.848** | (0.428) |
| Inflation, consumer prices (annual %) | −0.001 | (0.001) | Current account balance (% of GDP) | −0.061*** | (0.019) | CPIA score | −0.191 | (0.179) |
| ELF85 (Roeder) | 0.169 | (0.431) | Inflation, consumer prices (annual %) | 0.001 | (0.001) | Current account balance (% of GDP) | −0.035** | (0.015) |
| Regional fixed effects | yes | – | ELF85 (Roeder) | 0.255 | (0.481) | Inflation, consumer prices (annual %) | 0.001 | (0.001) |
|  |  |  | Regional fixed effects | yes | – | ELF85 (Roeder) | −0.063 | (0.358) |
|  |  |  |  |  |  | Regional fixed effects | yes | – |

- N 147

- Log-likelihood −579.011

- Significance levels: *10 % **: 5 % ***: 1 %; no intercept reported. Model estimated with FGLS due to maximization problems with MLE

About this article

Cite this article

Smets, L., Knack, S. & Molenaers, N. Political ideology, quality at entry and the success of economic reform programs. Rev Int Organ 8, 447–476 (2013). https://doi.org/10.1007/s11558-013-9164-2

Download citation

- Published06 March 2013

- Issue dateDecember 2013

- DOIhttps://doi.org/10.1007/s11558-013-9164-2

Keywords

- Development policy lending

- World Bank

- Political ideology

- Heckman selection model

- Triangular system of equations

JEL Classification

- C24

- C30

- O16

- O19

Article Navigation

Article Navigation

Journal Article

A Puzzle with Missing Pieces: Explaining the Effectiveness of World Bank Development Projects

Get access

Louise Ashton ,

Jed Friedman ,

Diana Goldemberg ,

Mustafa Zakir Hussain ,

Thomas Kenyon ,

Akib Khan ,

Mo Zhou

The World Bank Research Observer, Volume 38, Issue 1, February 2023, Pages 115–146, https://doi.org/10.1093/wbro/lkac005

Published:

12 July 2022

Article history

- Cite

- Permissions Icon Permissions

- Share Icon Share

Abstract

The identification of key determinants of aid effectiveness is a long-standing question in the development community. This paper reviews the literature on aid effectiveness at the project level and then extends the inquiry in a variety of dimensions with new data on World Bank investment project financing. It confirms that the country institutional setting and quality of project supervision are associated with project success, as identified previously. However, many aspects of the development project cycle, especially project design, have been difficult to measure and therefore under-investigated. The paper finds that project design, as proxied by the estimated value added of design staff, the presence of prior analytic work, and other specially collected measures, is a significant predictor of ultimate project success. These factors generally grow in predictive importance as the income level of the country rises. The results also indicate that a key determinant of the staff's contribution is their experience with previous World Bank projects, but not other characteristics such as age, education, or country location. Key inputs to the project production process associated with subsequent performance are not captured in routine data systems, although it is feasible to do so. Further, the conceptualization and measurement of the success of project-based aid should be revisited by evaluative bodies to reflect a project's theorized contribution to development outcomes.

JEL

H43 - Project Evaluation; Social Discount RateO22 - Project Analysis

Issue Section:

Article

© 2022 International Bank for Reconstruction and Development / The World Bank. Published by Oxford University Press

This article is published and distributed under the terms of the Oxford University Press, Standard Journals Publication Model (https://academic.oup.com/journals/pages/open_access/funder_policies/chorus/standard_publication_model)

You do not currently have access to this article.

Sign in

Get help with access

Personal account

- Sign in with email/username & password

- Get email alerts

- Save searches

- Purchase content

- Activate your purchase/trial code

- Add your ORCID iD

Sign in Register

Institutional access

Sign in through your institution

- Sign in with a library card

- Sign in with username/password

- Recommend to your librarian

Institutional account management

Sign in as administrator

Purchase

Subscription prices and ordering for this journal

Purchasing options for books and journals across Oxford Academic

Short-term Access

To purchase short-term access, please sign in to your personal account above.

Don't already have a personal account? Register

A Puzzle with Missing Pieces: Explaining the Effectiveness of World Bank Development Projects - 24 Hours access

EUR €39.00

GBP £33.00

USD $43.00

Rental

This article is also available for rental through DeepDyve.

Citations

8

Views

1,289

Altmetric

More metrics information

Email alerts

New journal issues

New journal articles

Activity related to this article

Sign up for marketing

Recommended

- Project Evaluation and Uncertainty in Practice: A Statistical Analysis of Rate-of-Return Divergences of 1,015 World Bank Projects

Gerhard Pohl, The World Bank Economic Review, 1992

- Project Evaluations: Learning What Works

Mark T. Buntaine, Oxford Academic Books, 2016

- Giving Aid Effectively: The Politics of Environmental Performance and Selectivity at Multilateral Development Banks

Mark T Buntaine, Oxford Academic Books, 2016

- Taking the Measure of Global Aid

Severino, Current History, 2010

- International Agencies for Development

Arnold Rivkin, Current History, 1966

- Lack of foreign aid effectiveness in developing countries between a hammer and an anvil

Elayah, Contemporary Arab Affairs, 2016

Powered by

Citing articles via

Web of Science (5)

Google Scholar

- Latest

- Most Read

- Most Cited

Participation in Pension Programs in Low- and Middle-Income Countries

The Impact of Infrastructure on Development Outcomes: A Meta-Analysis

Edutainment to Prevent Violence Against Women and Children

Firm-Level Adaptation to Climate Change in Low- and Middle-Income Countries

Migration, Growth, and Poverty Reduction in Rural China: Retrospect and Prospects

More from Oxford Academic

Development Planning and Policy

Economic Development and Growth

Economics

Social Sciences

Books

Journals

Article Navigation

Article Navigation

Journal Article

International Bureaucrats and Organizational Performance. Country-Specific Knowledge and Sectoral Knowledge in World Bank Projects

Get access

Mirko Heinzel

International Studies Quarterly, Volume 66, Issue 2, June 2022, sqac013, https://doi.org/10.1093/isq/sqac013

Published:

15 April 2022

Article history

- Cite

- Permissions Icon Permissions

- Share Icon Share

Abstract

International organizations (IOs) try to incorporate policy-specific best practices and country-specific knowledge to increase well-informed decision-making. However, the relative contribution of the two kinds of knowledge to organizational performance is insufficiently understood. The article addresses this gap by focusing on the role of staff in World Bank performance. It posits that country-specific knowledge, sectoral knowledge, and their combination positively contribute to World Bank projects. The argument is tested drawing on a novel database on the tenure, nationality, and educational background of World Bank Task Team Leaders. Three findings stand out. First, country-specific knowledge seems to matter on average, while sectoral knowledge does not. Second, there is some evidence that staff that combine both kinds of knowledge are empowered to make more positive contributions to performance. Third, the diversity and relevance of experience, not length of tenure, are associated with more success. The findings contribute to discussions on international bureaucracies by highlighting how differences between the knowledge of individual staff shape their decision-making and performance. IOs could better tap into the existing resources in their bureaucracies to enhance their performance by rotating staff less frequently between duty stations.

Las organizaciones internacionales (OOII) intentan incorporar las mejores prácticas específicas de las políticas y los conocimientos específicos de cada país para incrementar la toma de decisiones bien informada. Sin embargo, no se conoce bien la contribución relativa de estos dos tipos de conocimiento para el rendimiento de las organizaciones. En este artículo se aborda esta laguna al centrarse en el papel del personal en el rendimiento del Banco Mundial. En el artículo se afirma que los conocimientos específicos de cada país, los conocimientos de la industria y su combinación contribuyen a los proyectos del Banco Mundial de forma positiva. El argumento se pone a prueba mediante el uso de una novedosa base de datos sobre el cargo, la nacionalidad y la formación de los líderes de los equipos de trabajo del Banco Mundial. Se destacan tres hallazgos. Primero, los conocimientos específicos de cada país parecen ser relevantes en promedio, mientras que los conocimientos de la industria no lo son. Segundo, existen algunas pruebas de que el personal que combina ambos tipos de conocimiento está capacitado para realizar contribuciones más positivas al rendimiento. Tercero, la diversidad y la relevancia de la experiencia y no la duración del cargo parecen contribuir al éxito. Estos hallazgos contribuyen a debates sobre las burocracias internacionales al señalar cómo las diferencias entre los conocimientos de los distintos miembros del personal condicionan su toma de decisiones y rendimiento. Las OOII podrían aprovechar mejor los recursos existentes en sus burocracias para mejorar su productividad mediante una rotación menos frecuente de personal entre las estaciones de trabajo.

Les organisations internationales (OI) essaient d'intégrer des meilleures pratiques propres à chaque politique et des connaissances spécifiques à chaque pays afin de prendre des décisions mieux éclairées. Cependant, la contribution relative des deux types de connaissances aux performances organisationnelles est insuffisamment comprise. Cet article aborde cette lacune en se concentrant sur le rôle du personnel dans les performances de la Banque mondiale. Il postule que les connaissances spécifiques à chaque pays, les connaissances sectorielles et leur combinaison contribuent positivement aux projets de la Banque mondiale. Cet argument est mis à l’épreuve à l'aide d'une nouvelle base de données sur le mandat, la nationalité et la formation scolaire des chefs des groupes de travail de la Banque mondiale. Trois constatations se démarquent. D'abord, les connaissances spécifiques à chaque pays semblent en moyenne avoir de l'importance alors que les connaissances sectorielles n'en ont pas. Ensuite, nous avons décelé certaines preuves indiquant que le personnel combinant les deux types de connaissances avait ainsi la capacité d'apporter des contributions plus positives aux performances. Enfin, la diversité et la pertinence de l'expérience, et non la durée du mandat, semblent contribuer à la réussite. Ces constatations contribuent aux discussions sur les bureaucraties internationales en soulignant la manière dont les différences entre les connaissances de chaque membre du personnel façonnent leur prise de décisions et leurs performances. Les OI pourraient mieux puiser dans les ressources existantes de leurs bureaucraties pour améliorer leurs performances en faisant moins souvent tourner leur personnel entre les lieux d'affectation.

Issue Section:

Original Article

Collection: ISA Journals

© The Author(s) (2022). Published by Oxford University Press on behalf of the International Studies Association.

This article is published and distributed under the terms of the Oxford University Press, Standard Journals Publication Model (https://academic.oup.com/journals/pages/open_access/funder_policies/chorus/standard_publication_model)

You do not currently have access to this article.

Sign in

Get help with access

International Studies Association members

Sign in through society site

Personal account

- Sign in with email/username & password

- Get email alerts

- Save searches

- Purchase content

- Activate your purchase/trial code

- Add your ORCID iD

Sign in Register

Institutional access

Sign in through your institution

- Sign in with a library card

- Sign in with username/password

- Recommend to your librarian

Institutional account management

Sign in as administrator

Purchase

Subscription prices and ordering for this journal

Purchasing options for books and journals across Oxford Academic

Short-term Access

To purchase short-term access, please sign in to your personal account above.

Don't already have a personal account? Register

International Bureaucrats and Organizational Performance. Country-Specific Knowledge and Sectoral Knowledge in World Bank Projects - 24 Hours access

EUR €40.00

GBP £34.00

USD $44.00

Rental

This article is also available for rental through DeepDyve.

Advertisement

Citations

38

Views

1,570

Altmetric

More metrics information

Email alerts

New journal issues

New journal articles

Activity related to this article

Sign up for marketing

Recommended

- Assessing the influence of knowledge translation platforms on health system policy processes to achieve the health millennium development goals in Cameroon and ...

Pierre Ongolo-Zogo, Health Policy and Planning, 2018

- Preface

Aradhna Aggarwal, Oxford Academic Books, 2012

- Pathologies of a Different Kind: Dysfunctional Interactions between International Organizations

Matthias Kranke, Global Studies Quarterly, 2022

- To mature or not to mature : the information systems conundrum

Carl Marnewick, South African Computer Journal, 2013

- Needs of parenting interventions based on mobile health technology in parents of depressed adolescents: A qualitative study

HU Yiwen TIAN Dan LIU Chun XIE Simin YANG Min, Journal of Central South University(Medical Science), 2025

- Big Data Driven Decision Making Model: A case of the South African banking sector

Komla Pillay, South African Computer Journal, 2021

Powered by

Citing articles via

Web of Science (27)

Google Scholar

- Latest

- Most Read

- Most Cited

Today Ukraine, Tomorrow Taiwan? Assessing US Reputation and Deterrence across International Crises

Preserve, Pressure, Protect, and Peel: The US–China Rivalry and the Politics of Vaccine Provision

Global Governance by Manual: The Transitional Justice Toolkit and the Standardization of a Field

Populist Publics’ Affinity for Nuclear Weapons? Explaining Opposition to the Nuclear Sharing Weapons in European Populist Publics

The Consequences of Violence for Women’s Candidacy in Legislative Elections: Insights from a Global Analysis